## Task Time Log
Date | Day | Jira Ticket | Task / Work Done | Time Spent (Hrs)
2026-09-07 | Monday | VGP-10893 / SMS Monitor | Downloaded/opened the project files and set up the SMS Monitor project. Studied the code, database flow and existing SMS synchronization to understand the reported issues. | 3
2026-09-07 | Monday | VGP-10893 | Investigated hy the SMS count was different from the original SMS source data and checked the existing calculation logic. | 3
2026-09-07 | Monday | VGP-10893 | Started working on the SMS synchronization and count mismatch fix. | 2
2026-09-08 | Tuesday | VGP-10893 | Changed the SMS count calculation to use the actual SMS records and worked on daily synchronization by client and usage date. | 4
2026-09-08 | Tuesday | VGP-10893 | Removed the old 30-day synchronization restriction and updated the UsedSMS calculation. | 2
2026-09-08 | Tuesday | VGP-10893 | Tested the changes against the source SMS data and checked the application count. | 2
2026-09-09 | Wednesday | VGP-10893 | Continued testing the SMS count fix and checked source count, synchronized daily count and application UsedSMS values. | 3
2026-09-09 | Wednesday | VGP-10894 | Started investigating the detailed SMS report download issue and studied the existing report generation flow. | 3
2026-09-09 | Wednesday | VGP-10894 | Started implementing the detailed SMS report generation using individual records from Smslog_Vtb. | 2
2026-09-10 | Thursday | VGP-10893 | Completed validation of the SMS count mismatch fix. Verified VTPL_WEB source, synchronized and application counts matched at 180,956. | 2
2026-09-10 | Thursday | VGP-10894 | Completed detailed SMS report generation and download API. Added date filtering and generated the Excel report successfully. | 4
2026-09-10 | Thursday | VGP-10894 | Tested the downloaded report and checked the report data and download flow. | 2
2026-09-11 | Friday | VGP-10894 | Updated the detailed SMS report to use the provided SMS Report Excel template and checked the required report fields/format. | 3
2026-09-11 | Friday | VGP-10895 | Investigated the historical/past SMS data issue and checked why older records were not being captured. | 2
2026-09-11 | Friday | VGP-10895 | Removed the historical date restriction and updated synchronization to capture historical SMS records into the daily usage table. | 2
2026-09-11 | Friday | VGP-10895 | Tested historical data capture and verified the historical date range and synchronized records. | 1
2026-09-14 | Monday | VGP-10922 | Downloaded and set up the latest SMS Monitor folder shared by RobinSon Sir. Studied the new project structure and compared it with the previous working version. | 3
2026-09-14 | Monday | VGP-10922 | Checked database connectivity. Confirmed 10.1.1.194:1433 was reachable and updated the .env database IP from 10.200.9.4 to 10.1.1.194. | 3
2026-09-14 | Monday | VGP-10922 | Verified the database connection and ran the project after the configuration change. | 2
2026-09-15 | Tuesday | VGP-10922 | Fixed the Python virtual-environment/Uvicorn startup issue and confirmed the project was running. | 2
2026-09-15 | Tuesday | VGP-10922 | Investigated the dashboard UI issue where CSS, images and styling were not loading correctly. | 4
2026-09-15 | Tuesday | VGP-10922 | Worked on the UI/static-file issue and tested the dashboard. | 2
2026-09-16 | Wednesday | VGP-10922 | Tested login and verified both Admin and Viewer credentials were working and redirecting to the dashboard. | 2
2026-09-16 | Wednesday | VGP-10922 | Checked the dashboard buttons/icons and investigated the non-working Analytics section. | 2
2026-09-16 | Wednesday | VGP-10922 | Compared the new project with the previous version to identify the missing pages, permissions and dashboard functionality. | 4
2026-09-17 | Thursday | VGP-10922 | Implemented/updated Admin and Viewer access and related dashboard pages/permissions. | 3
2026-09-17 | Thursday | VGP-10922 | Worked on Analytics, graphs/charts and client analytics functionality. | 3
2026-09-17 | Thursday | VGP-10922 | Tested the implemented functionality and fixed related issues. | 2
2026-09-18 | Friday | VGP-10922 | Completed dashboard and access-control functionality and worked on SMS trends and client usage reporting. | 3
2026-09-18 | Friday | VGP-10922 | Worked on audit logging, email reports and detailed SMS report download functionality. | 2
2026-09-18 | Friday | VGP-10922 | Worked on Excel report generation and final functionality testing. | 3
2026-09-19 | Saturday | VGP-10922 | Performed final testing and validation of the completed SMS Monitor functionality. | 2
2026-09-19 | Saturday | VGP-10922 | Prepared/updated the implementation report and screenshot evidence. | 2
2026-09-19 | Saturday | VGP-10922 | Updated the Jira sub-task with the completed implementation and evidence, and prepared the work for Sir's review/demo. | 2
|  |  | TOTAL HOURS | 86
Total Hours | 86 hours

## Ticket Summary
Jira Ticket | Work | Date | Notes
VGP-10893 | SMS counts not matching original data | 10-Sep-2026 | Work and validation completed; Jira evidence updated.
VGP-10894 | Detailed SMS report download | 10-Sep-2026 / 11-Sep-2026 | Implementation completed on 10 Sep; Excel template/format updated and evidence added on 11 Sep.
VGP-10895 | Historical/past SMS data not captured | 11-Sep-2026 | Historical synchronization fix and validation completed.
VGP-10922 | Complete SMS Monitor Dashboard Functionality and Access Control | 19-Sep-2026 | Implementation report and screenshot evidence uploaded; work completed and submitted for review.

## Notes
Timesheet Notes
Included dates | 07-Sep to 11-Sep, 14-Sep to 18-Sep, and 22-Sep 2026. Weekends and 21-Sep holiday excluded.
Time format | Daily work is split into simple tasks. Total is based on the hours entered for each task.
Important | Ticket dates reflect the work/update information provided: VGP-10893 validated on 10 Sep, VGP-10894 implemented on 10 Sep and template update on 11 Sep, VGP-10895 completed on 11 Sep, and VGP-10922 updated with the final report on 19 Sep.
Total project hours | 88 hours